## TASK_TRACKER
Task ID | Date Created | Department | Process Area | Task Description | Task Type | Owner Name | Dependency | Status | Priority | Start Date | Due Date | Days Open | Delay Status | Blocker Reason | Next Action | Escalation Level | Last Update
T001 | Today | Purchase | Raw Material | PO Approval Pending | Unplanned | Raj | Finance Approval | In Progress | High | Today | Tomorrow | #VALUE! | ON TRACK | Waiting For Approval | Follow up with finance | Level 2 | Today
T002 |  | Quality |  | OOS investigation |  |  |  | Blocked | High |  | Yesterday | 46177 | ON TRACK
T003 |  | Maintenance |  | Machine Repair |  |  |  | Not Started | Medium |  | Today | 46177 | ON TRACK
Formulas:
Days Open = TODAY()-[Start Date]
Delay Status = IF(TODAY()>[Due Date],"OVERDUE","ON TRACK")

## DASHBOARD
TOTAL TASKS | OVERDUE TASKS | BLOCKED TASKS | UNPLANNED WORK
3 | 0 | 1 | 1
Purchase Due | 0
Quality Overdue | 0
Maintenance Overdue | 0

## DROPDOWNS
Departments | Status | Priority | Task Type
Purchase | Not Started |  | Planned
Warehouse | In Progress |  | Unplanned
Quality | Blocked |  | Routine
Production | Completed
Maintenance | Escalated
HR
IT
R&D